## Team-C - Product Backlog
Title | URL | Milestone | Deliverable / Sprint | User Story | Story Type | Priority | Estimate (Story Points) | Status
As a new software developer, I would like to interact with and post questions on a board private to my company, so that I may address common job specific issues. | https://github.com/COS420-F25/TeamC/issues/71 |  |  | Yes | Requirements | High | 2 | Product Backlog
As a junior developer, I would like to be able to respond to feedback I receive so that I may acknowledge if it has solved the problem. | https://github.com/COS420-F25/TeamC/issues/58 |  |  | Yes | Requirements | High | 1 | Product Backlog
As a new developer, I would like to ask questions anonymously to senior developer coworkers, so that I may spend less time waiting for an answer | https://github.com/COS420-F25/TeamC/issues/56 |  |  | Yes | Requirements | High | 2 | Product Backlog
As a new developer, I would like to interact on a public forum with people at the same company, so that I may build confidence for my own personal workspace. | https://github.com/COS420-F25/TeamC/issues/72 |  |  | Yes | Requirements | Medium | 1 | Product Backlog
As a junior developer, I would like to chat personally with those that I may need to speak to, so that i may get more in detail about a publicly addressed problem or to chat with others at my same company. | https://github.com/COS420-F25/TeamC/issues/73 |  |  | Yes | Requirements | Medium | 1 | Product Backlog
As a new developer, I would like to view past discussions to see if my questions have been answered in the past, so that I don’t have to wait on current responses. | https://github.com/COS420-F25/TeamC/issues/67 |  |  | Yes | Requirements | Medium | 3 | Product Backlog
As a senior developer, I would like to be able to answer other developers' questions so that I can help them learn best practices at our company. | https://github.com/COS420-F25/TeamC/issues/62 |  |  | Yes | Requirements | Medium | 2 | Product Backlog
As a new hire, I would like to be able to quickly find solutions to known problems, so that I can solve problems faster that may have been encountered before. | https://github.com/COS420-F25/TeamC/issues/60 |  |  | Yes | Requirements | Medium | 1 | Product Backlog
As a new developer, I would like to have easy access to answers to questions that are common among my team, so that we can quickly handle them. | https://github.com/COS420-F25/TeamC/issues/57 |  |  | Yes | Requirements | Medium | 1 | Product Backlog
As a senior developer. I would like to get notifications for new questions in my workspace that may appear so that I can swiftly answer them. | https://github.com/COS420-F25/TeamC/issues/75 |  |  | Yes | Requirements | Medium |  | Product Backlog
As a developer, I would like to be able to ask for feedback from other developers about my work, so that I know what tips people could give me to improve. | https://github.com/COS420-F25/TeamC/issues/59 |  |  | Yes | Requirements | Low | 1 | Product Backlog
As a new developer, I would like to discuss my work with others and improve it, so that I can perform better in the future. | https://github.com/COS420-F25/TeamC/issues/63 |  |  | Yes | Requirements | Low | 1 | Product Backlog
As a developer, I would like to report any questions that are “improper”, so that it can be removed by a project manager. | https://github.com/COS420-F25/TeamC/issues/64 |  |  | Yes | Requirements | Low | 2 | Product Backlog
As a project manager, I would like to remove reported questions and then see who posted them, so that I can ensure a comfortable environment for everyone. | https://github.com/COS420-F25/TeamC/issues/65 |  |  | Yes | Requirements | Low | 2 | Product Backlog
As a team lead, I would like to be able to have access to a screen where I can organize all questions asked in a given help board, so that I can identify where they need more training. | https://github.com/COS420-F25/TeamC/issues/61 |  |  | Yes | Requirements | Low | 3 | Product Backlog
As a developer, I want to be able to be “rewarded” for correctly answering others' questions, so that I have incentive to do so. | https://github.com/COS420-F25/TeamC/issues/66 |  |  | Yes | Requirements | Low | 3 | Product Backlog