## Team-C - Sprint Backlog
Title | URL | Status | Priority | Story Type | Estimate (Story Points) | Points Completed | Assignees | Contributors and % contribution | Quality Reviewer | Start date | End date (ready for QC by) | Deliverable / Sprint | Milestone
As a junior developer, I would like to be able to respond to feedback I receive so that I may acknowledge if it has solved the problem. | https://github.com/COS420-F25/TeamC/issues/58 | Done | High | Requirements | 1 | [6 empty] | Deliverable 3
As a new software developer, I would like to interact with and post questions on a board private to my company, so that I may address common job specific issues. | https://github.com/COS420-F25/TeamC/issues/71 | Todo / Sprint Backlog | High | Requirements | 2 | [6 empty] | Deliverable 3
Split up current tasks | https://github.com/COS420-F25/TeamC/issues/110 | Done |  |  |  |  | Nicugh |  |  |  |  | Deliverable 3 | Deliverable 3 -Work Complete-
Break up revisions when available | https://github.com/COS420-F25/TeamC/issues/109 | Done |  |  |  |  | Nicugh |  |  |  |  | Deliverable 3
Design "Class Diagram" | https://github.com/COS420-F25/TeamC/issues/104 | Done |  |  |  |  | Nathan-R-Wheeler |  |  |  |  | Deliverable 3
Domain Model | https://github.com/COS420-F25/TeamC/issues/105 | Done |  |  |  |  | Nathan-R-Wheeler |  |  |  |  | Deliverable 3
(optional)Usability Testing | https://github.com/COS420-F25/TeamC/issues/106 | Todo / Sprint Backlog |  |  | 1 | [6 empty] | Deliverable 3 | Deliverable 3 -Work Complete-
Continous Intergration | https://github.com/COS420-F25/TeamC/issues/108 | Todo / Sprint Backlog | [9 empty] | Deliverable 3
Create Video | https://github.com/COS420-F25/TeamC/issues/107 | Todo / Sprint Backlog |  |  | 2 | [6 empty] | Deliverable 3 | Deliverable 3 -Work Complete-
Draft writeup for domain model | https://github.com/COS420-F25/TeamC/issues/111 | Done | [9 empty] | Deliverable 3 | Deliverable 3 -Work Complete-
Add Flag Content to Use case | https://github.com/COS420-F25/TeamC/issues/112 | Done |  |  |  |  | Nathan-R-Wheeler |  |  |  |  | Deliverable 3 | Deliverable 3 -Work Complete-
Fix Search Questions | https://github.com/COS420-F25/TeamC/issues/113 | Done |  |  | 1 | [6 empty] | Deliverable 3 | Deliverable 3 -Submission-
Clarify terminology in the use case descriptions | https://github.com/COS420-F25/TeamC/issues/114 | Done |  |  | 1 |  | Nathan-R-Wheeler |  |  |  |  | Deliverable 3 | Deliverable 3 -Work Complete-
Revise Architecture design document | https://github.com/COS420-F25/TeamC/issues/115 | Done | [9 empty] | Deliverable 3 | Deliverable 3 -Submission-
Listen to Dr. Greg's discord feedback more closely | https://github.com/COS420-F25/TeamC/issues/116 | Done |  |  |  |  | Nathan-R-Wheeler |  |  |  |  | Deliverable 3 | Deliverable 3 -Work Complete-
Make changes to UI mockup | https://github.com/COS420-F25/TeamC/issues/119 | Todo / Sprint Backlog |  |  |  |  | Nathan-R-Wheeler |  |  |  |  | Deliverable 3 | Deliverable 3 -Submission-
Finish Sprint Review | https://github.com/COS420-F25/TeamC/issues/120 | Done |  |  |  |  | Nathan-R-Wheeler |  |  |  |  | Deliverable 3 | Deliverable 3 -Work Complete-