## Team-C - Product Backlog (1)
Title | URL | Milestone | Deliverable / Sprint | User Story | Story Type | Priority | Estimate (Story Points) | Status
As a junior developer, I would like to be able to respond to feedback I receive so that I may acknowledge if it has solved the problem. | https://github.com/COS420-F25/TeamC/issues/58 |  | Deliverable 3 | Yes | Requirements | High | 1 | Done
As a new software developer, I would like to interact with and post questions on a board private to my company, so that I may address common job specific issues. | https://github.com/COS420-F25/TeamC/issues/71 |  | Deliverable 3 | Yes | Requirements | High | 2 | Todo / Sprint Backlog
Split up current tasks | https://github.com/COS420-F25/TeamC/issues/110 | Deliverable 3 -Work Complete- | Deliverable 3 |  |  |  |  | Done
Break up revisions when available | https://github.com/COS420-F25/TeamC/issues/109 |  | Deliverable 3 |  |  |  |  | Done
Design "Class Diagram" | https://github.com/COS420-F25/TeamC/issues/104 |  | Deliverable 3 |  |  |  |  | Done
Domain Model | https://github.com/COS420-F25/TeamC/issues/105 |  | Deliverable 3 |  |  |  |  | Done
(optional)Usability Testing | https://github.com/COS420-F25/TeamC/issues/106 | Deliverable 3 -Work Complete- | Deliverable 3 |  |  |  | 1 | Todo / Sprint Backlog
Continous Intergration | https://github.com/COS420-F25/TeamC/issues/108 |  | Deliverable 3 |  |  |  |  | Todo / Sprint Backlog
Create Video | https://github.com/COS420-F25/TeamC/issues/107 | Deliverable 3 -Work Complete- | Deliverable 3 | No |  |  | 2 | Todo / Sprint Backlog
Draft writeup for domain model | https://github.com/COS420-F25/TeamC/issues/111 | Deliverable 3 -Work Complete- | Deliverable 3 |  |  |  |  | Done
Add Flag Content to Use case | https://github.com/COS420-F25/TeamC/issues/112 | Deliverable 3 -Work Complete- | Deliverable 3 |  |  |  |  | Done
Fix Search Questions | https://github.com/COS420-F25/TeamC/issues/113 | Deliverable 3 -Submission- | Deliverable 3 |  |  |  | 1 | Done
Clarify terminology in the use case descriptions | https://github.com/COS420-F25/TeamC/issues/114 | Deliverable 3 -Work Complete- | Deliverable 3 |  |  |  | 1 | Done
Revise Architecture design document | https://github.com/COS420-F25/TeamC/issues/115 | Deliverable 3 -Submission- | Deliverable 3 |  |  |  |  | Done
Listen to Dr. Greg's discord feedback more closely | https://github.com/COS420-F25/TeamC/issues/116 | Deliverable 3 -Work Complete- | Deliverable 3 |  |  |  |  | Done
Make changes to UI mockup | https://github.com/COS420-F25/TeamC/issues/119 | Deliverable 3 -Submission- | Deliverable 3 |  |  |  |  | Todo / Sprint Backlog
Finish Sprint Review | https://github.com/COS420-F25/TeamC/issues/120 | Deliverable 3 -Work Complete- | Deliverable 3 |  |  |  |  | Done